EduCheck

A Rule-Based Web and Mobile System for Academic Record Consolidation, Validation, and Submission in Government Elementary Schools

Software Project Management Plan (SPMP)

Capstone Project II  ·  Methodology: Agile-Kanban

Version 1.0

Status: Draft — Pending Adviser Review

Prepared by

Marjorie Gale Arizo

Aira Jeanelle Hepana

Shaine Ella Pines

Adviser: Engr. Roselyn A. Maaño & Donabell Hernandez

BS Information Technology  ·  2026

# Contents

Contents	2

1. Introduction	4

2. Product Vision and Goals	4

2.1 Vision Statement	4

2.2 Product Goal	4

2.3 Project Objectives	4

2.4 Target Users	5

2.5 Value Proposition	5

3. Problem Statement	5

4. Core Innovation Features	6

5. Proposed System Workflow	7

6. System Overview	8

6.1 System Modules	8

6.2 User Roles	8

6.3 Project Scope	9

6.4 Technology Stack	9

6.5 Mobile Application	10

7. Project Organization	11

7.1 Team Members	11

7.2 Responsibilities	12

7.3 Communication Plan	12

8. Product Planning	12

8.1 Product Roadmap	12

8.2 Project Epics	13

8.3 Features	13

8.4 Product Backlog	14

9. Agile-Kanban Management	15

9.1 Sprint Plan	15

9.2 Kanban Workflow	15

9.3 Definition of Ready (DoR)	15

9.4 Definition of Done (DoD)	16

10. Quality Management	16

10.1 Coding Standards	16

10.2 Code Review	16

10.3 Testing Strategy	16

11. Risk Management	17

12. Appendix	17

# 1. Introduction

EduCheck is a web and mobile academic record management system designed to modernize the preparation of student permanent records in government elementary schools. The system addresses the repetitive and error-prone process of manually transferring grades from official DepEd e-Class Records into the School Form 10 (SF10).

The project follows the Agile-Kanban methodology, enabling the development team to build the system incrementally while continuously validating each feature through sprint reviews and adviser consultations. This document is the primary project management reference throughout the development phase, and Version 1.0 reflects the consolidated workflow, role structure, and access-control model finalized for the project.

# 2. Product Vision and Goals

## 2.1 Vision Statement

EduCheck aims to modernize the academic record management process in government elementary schools by automating the consolidation, validation, generation, storage, and submission of student permanent records while preserving the existing DepEd e-Class Record workflow. Rather than replacing current grading practices, EduCheck enhances them by reducing repetitive manual work, minimizing encoding errors, improving data accuracy, and supporting more efficient academic record management.

## 2.2 Product Goal

Develop a reliable web and mobile academic record management system that automates the consolidation, validation, generation, storage, and submission of student permanent records while preserving the existing DepEd e-Class Record workflow.

## 2.3 Project Objectives

- Reduce repetitive encoding performed by teachers.

- Automate academic record preparation.

- Preserve the official DepEd grading workflow.

- Improve the accuracy and consistency of academic records.

- Support school administrators in monitoring submissions.

- Digitize permanent student records for easier retrieval.

- Provide analytics to assist academic intervention and school decision-making.

- Enforce subject- and section-level access control so each user only encodes or views data within their own responsibility.

- Let each school configure its own staffing pattern per section (self-contained or departmentalized) rather than assuming a fixed rule by grade level.

## 2.4 Target Users

| User | Responsibilities |
| --- | --- |
| Subject Teacher | For a departmentalized section: uploads the official e-Class Record for their assigned subject and section; reviews validation results and fixes flagged entries by correcting the e-Class Record file and re-uploading it, within that subject only. (Assigned per section by the Administrator — not tied to a fixed grade level.) |
| Class Adviser | For a self-contained section: uploads e-Class Records for every learning area, since they are the only teacher assigned. For a departmentalized section: reviews the consolidated record, returns a subject for correction if needed, and submits the section for approval. Whether a section is self-contained or departmentalized is configured per section by the Administrator. |
| School Administrator | Approves or returns submitted class records; adds user accounts, which can be used only after the Principal approves them, and manages subject/section assignments; oversees the digital repository and the school and SF10 settings. |
| Principal | Monitors submission progress, school-wide analytics, and reports across all sections and grade levels (view-only), and approves or rejects new user accounts and role changes that give more access. |

## 2.5 Value Proposition

### For Teachers

- Eliminates repetitive grade transfer.

- Reduces encoding errors.

- Saves time preparing SF10.

### For Schools

- Standardizes academic record management.

- Improves data quality.

- Digitizes permanent records.

### For Administrators

- Simplifies approval and monitoring.

- Provides academic analytics.

- Improves record accessibility.

### For Principals

- Real-time, school-wide visibility into submission progress and academic performance without requesting manual reports.

# 3. Problem Statement

Government elementary schools currently use separate official DepEd e-Class Record spreadsheets for each subject. Although these spreadsheets automatically compute grades, teachers still manually transfer the final grades into individual SF10 permanent records. This manual process is time-consuming, repetitive, and susceptible to human error. Additionally, retrieving student records from multiple files can be inefficient.

EduCheck addresses these challenges by preserving the official DepEd workflow while automating record consolidation, validation, SF10 generation, and digital record management — with access to each subject's data restricted to the teacher responsible for it.

# 4. Core Innovation Features

### Flagship Innovation

Automated Academic Record Consolidation and SF10 Generation using Rule-Based Validation from Official DepEd e-Class Records.

### Supporting Innovations

### 1. Direct Import of Official DepEd e-Class Records

- Upload existing DepEd Excel files.

- No duplicate encoding.

- No changes to the official grading format.

### 2. Automatic Multi-Subject Grade Consolidation

- Consolidates grades from multiple subject files.

- Uses the Learner Reference Number (LRN) as the primary identifier.

### 3. Rule-Based Validation Engine

- Automatically detects missing grades, invalid grade values, duplicate learners, incorrect averages, and incomplete records.

### 4. Automatic SF10 Generation

- Automatically generates each student's permanent record after successful validation.

### 5. Submission Readiness Assessment

- Verifies that all required information is complete before submission.

### 6. Academic Analytics Dashboard

- Provides student performance summaries, submission progress, and intervention monitoring.

### 7. Digital Permanent Record Repository

- Allows authorized users to search records by LRN, Student Name, Grade Level, or School Year.

### 8. Offline Status Caching (Mobile)

- On the mobile app, the last-synced submission statuses and notifications stay viewable without a connection and refresh once access is restored (M-10). Uploading or reviewing records offline on the web is out of scope.

### 9. Subject-Based Role Access Control (RBAC)

- Restricts each Subject Teacher to their own assigned subject and section.

- Advisers and Administrators see broader, role-appropriate views.

- Preserves accountability — a grade can only be edited by the teacher who submitted it. Grades from school years before EduCheck, which no teacher uploaded, are entered by the Adviser or Administrator on the learner's permanent record (US-014).

### 10. Configurable Section Staffing Model

- Each section is set by the Administrator as Self-Contained or Departmentalized — the system does not assume a fixed rule by grade level.

- Fits any school's actual staffing pattern, including partial departmentalization (e.g. only Grade 6, or only specific subjects).

# 5. Proposed System Workflow

### Existing Workflow

Subject Teacher

↓

Encode Grades in Official DepEd e-Class Record

↓

Automatic Grade Computation

↓

Manually Transfer Grades to SF10

↓

Review

↓

Submit

Existing Problems:

- Manual grade transfer

- Duplicate work

- Human errors

- Time-consuming preparation

- Separate Excel files for every subject

### Proposed EduCheck Workflow

Whether a section is Self-Contained or Departmentalized is configured per section by the Administrator, not derived from grade level — the same section-level setting applies however a particular school actually staffs each grade.

Subject Teacher (departmentalized section) or Class Adviser (self-contained section)

↓

Complete Official DepEd e-Class Record

↓

Upload Excel File (assigned subject and section only)

↓

Automatic File Reading

↓

Rule-Based Validation

↓

Automatic Grade Consolidation (by LRN, across all subjects in the section)

↓

Adviser Review (approve, or return a subject for correction)

↓

Automatic SF10 Generation

↓

Submission Readiness Check

↓

Administrator Review and Approval

↓

Digital Repository

↓

Analytics Dashboard

# 6. System Overview

## 6.1 System Modules

| Module | Purpose |
| --- | --- |
| Authentication & User Management | Secure login, role management, Principal approval of new accounts, and emailed temporary passwords |
| Section Staffing Configuration | Administrator sets each section as Self-Contained or Departmentalized and assigns teachers accordingly |
| Role & Subject Access Control | Enforces subject- and section-level access restrictions per user role, based on that section's configured staffing mode |
| e-Class Record Import | Upload and parse official Excel files |
| Academic Record Consolidation | Merge subject records into one student record |
| Rule-Based Validation | Validate grades and detect inconsistencies |
| SF10 Generation | Generate permanent records automatically |
| Submission Workflow | Review, approve, and track submissions |
| Notifications | Alert users when a submission's status changes and keep a notification history (web and mobile) |
| Digital Repository | Store and retrieve records |
| Academic Analytics | Generate reports and dashboards |

## 6.2 User Roles

| Role | Responsibilities | Access Scope |
| --- | --- | --- |
| Subject Teacher | Upload assigned subject's e-Class Record; review only their own validation results and fix flagged entries by re-uploading the corrected file. | One subject, assigned section(s) — only for sections configured as Departmentalized |
| Class Adviser | Self-Contained section: upload every subject for own section. Any section: review consolidated record, return a subject for correction, submit for approval. | Full visibility, own section only |
| School Administrator | Approve or return submissions; add user accounts and finish their setup after the Principal approves them; manage roles, subject/section assignments, and each section's staffing mode; configure school and SF10 settings. Validation rules follow DepEd Order No. 8, s. 2015 and are fixed by design; the Administrator can view them read-only. | Full system access |
| Principal | View submission progress, analytics, and repository. Approve or reject new accounts and role changes that give more access. | School-wide; view-only except account approval |

## 6.3 Project Scope

Included:

- User Authentication

- Role & Subject Access Control

- Excel Upload

- Excel Parsing

- Academic Record Consolidation

- Rule-Based Validation

- Automatic SF10 Generation

- Submission Workflow

- Notification System

- Digital Repository

- Analytics Dashboard

- Web Application

- Mobile Application (see §6.5)

Excluded:

- Attendance Management

- Payroll

- Enrollment System

- Modification of DepEd Grading Formula

- National DepEd Database Integration

- AI Grade Prediction

## 6.4 Technology Stack

| Layer | Technology |
| --- | --- |
| Web | React |
| Mobile | Flutter |
| Backend | Node.js + Express |
| Database | PostgreSQL |
| Authentication | JWT |
| File Processing | ExcelJS |
| Version Control | GitHub |
| Methodology | Agile-Kanban |

## 6.5 Mobile Application

The mobile application extends the EduCheck workflow beyond the desktop so that submission status, validation results, and approval actions are never locked behind a laptop. It remains, by design, a supplementary companion to the web platform — all record encoding, e-Class Record uploads, and settings stay on the web system — but within that boundary it gives every user role a reason to open it daily rather than only at their desk.

This scope is intentional: government elementary teachers and administrators do not need a second full platform to learn, and a lighter mobile footprint is realistic for a small development team to build and test well within the sprint plan. What the mobile app adds is timely visibility and lightweight decision-making — the two things that are genuinely painful to be without when away from a computer.

### Value Proposition by User Role

| User | What the mobile app gives them |
| --- | --- |
| Subject Teacher | Instant push alerts the moment rule-based validation flags an issue (missing grades, invalid values, duplicate learners), so revisions start immediately instead of waiting for the next browser session. |
| Class Adviser | A consolidated, on-the-go view of every subject teacher's submission status under their class, without chasing updates manually. |
| School Administrator | The ability to review and approve or return submissions from anywhere, so approval isn't a bottleneck tied to being at a desk. |
| Principal | A quick-glance snapshot of school-wide submission progress and analytics, usable during walkthroughs or off-site meetings. |

### Mobile Feature Set

| # | Feature | Description | Primary User(s) |
| --- | --- | --- | --- |
| M-01 | Secure Mobile Login | Same account and role-based access as the web platform (JWT); no separate registration. | All users |
| M-02 | Push Notifications | Real-time alerts for validation results, revision requests, approval/rejection, and SF10 generation completion. | Subject Teacher, Adviser |
| M-03 | Submission Status Dashboard | Live status per record — Uploaded → Consolidating → Validating → Needs Revision → Ready → Submitted → Approved. | Subject Teacher, Adviser |
| M-04 | Validation Error Summary (read-only) | View exactly what the rule-based engine flagged and why, to fix correctly on web. | Subject Teacher |
| M-05 | SF10 Preview | Read-only preview of a generated SF10 permanent record before formal submission. Subject Teachers are excluded because the SF10 shows every subject's grades. | Adviser, Administrator, Principal (read-only) |
| M-06 | Mobile Approval Action | Approve or return a submitted record directly from a notification or the dashboard. The Principal sees the same records read-only (SPMP §6.2). | Administrator |
| M-07 | Academic Analytics Snapshot | Simplified view of submission completion rate by section and outstanding items. | Principal, Administrator |
| M-08 | Digital Repository Lookup | Search a student's permanent record by LRN or name for quick reference. | Adviser, Administrator |
| M-09 | Notification History | A log of past alerts, so nothing is lost if a push notification is missed. | All users |
| M-10 | Offline Status Caching | Last-synced status and notifications remain viewable offline, auto-syncing once connectivity returns. | All users |
| M-11 | Adviser Review Actions | Submit a complete record for approval, or return one subject to its teacher with a reason, from the record view. Uploading stays on the web. | Class Adviser |

### Deliberately Out of Scope for Mobile

To keep the supplementary-tool positioning consistent with the manuscript and realistic for the project timeline, the following stay web-only:

- Uploading or parsing official DepEd e-Class Record Excel files

- Encoding or editing academic records and grades

- Viewing validation rules (they are fixed; the Administrator views them read-only on the web)

- Generating SF10 records (mobile only previews an already-generated SF10)

# 7. Project Organization

## 7.1 Team Members

| Member | Role |
| --- | --- |
| Shaine Ella Pines | Project Leader / Backend Developer / Documentation Lead |
| Marjorie Gale Arizo | Mobile App Developer |
| Aira Jeanelle Hepana | Frontend Developer |

Development role assignments for Marjorie Gale Arizo and Aira Jeanelle Hepana are provisional — confirm and adjust with the team as needed.

## 7.2 Responsibilities

| Role | Responsibilities |
| --- | --- |
| Project Leader | Sprint planning, Kanban board management, documentation, adviser coordination |
| Backend Developer | Database, APIs, validation engine, Excel processing |
| Frontend Developer | Web interface, dashboard, repository, analytics |

## 7.3 Communication Plan

| Activity | Frequency |
| --- | --- |
| Team Meeting | Weekly |
| Adviser Consultation | Every Sprint |
| Sprint Review | Every 2 Weeks |
| GitHub Update | Daily |
| Kanban Update | Daily |

# 8. Product Planning

## 8.1 Product Roadmap

| Sprint | Theme | Major Deliverables |
| --- | --- | --- |
| Sprint 1 | Project Foundation | Product Vision, Backlog, Kanban Board, Repository, System Design |
| Sprint 2 | User Management | Authentication and User Roles |
| Sprint 3 | e-Class Record Import | Upload, Parsing, Validation |
| Sprint 4 | Academic Record Consolidation | Grade Consolidation |
| Sprint 5 | Rule-Based Validation | Validation Engine |
| Sprint 6 | SF10 Generation | Automatic SF10 Generation |
| Sprint 7 | Workflow & Repository | Submission Workflow and Repository |
| Sprint 8 | Analytics & Integration | Dashboard and Reports |
| Sprint 9 | Testing & Deployment | Testing, Documentation, Final Deployment |

## 8.2 Project Epics

| Epic ID | Epic |
| --- | --- |
| EPIC-01 | Authentication & User Management |
| EPIC-02 | e-Class Record Import |
| EPIC-03 | Academic Record Consolidation |
| EPIC-04 | Rule-Based Validation |
| EPIC-05 | SF10 Generation |
| EPIC-06 | Submission Workflow |
| EPIC-07 | Digital Repository |
| EPIC-08 | Academic Analytics |
| EPIC-09 | System Integration & Testing |

## 8.3 Features

### EPIC-01 — Authentication & User Management

- Role-based secure login (JWT)

- Account and subject/section assignment management (Administrator), with Principal approval of new accounts and role raises, and an emailed temporary password that must be replaced at first sign-in (US-015)

- Per-section staffing configuration — Self-Contained or Departmentalized, set independently of grade level

### EPIC-02 — e-Class Record Import

- Drag-and-drop Excel upload per subject and section

- Template structure validation before parsing

### EPIC-03 — Academic Record Consolidation

- LRN-based matching across subject files

- Section consolidation status view showing submitted vs. pending subjects

### EPIC-04 — Rule-Based Validation

- Grade range and completeness checks

- Duplicate-LRN and incorrect-average detection

- Inline flagging of records needing correction

- Read-only list of the validation rules for the Administrator (rules are fixed, not configurable)

### EPIC-05 — SF10 Generation

- Automatic generation from a completed consolidated record

- Read-only SF10 preview before submission

### EPIC-06 — Submission Workflow

- Adviser review and return-to-teacher action

- Submit-for-approval and Administrator approve/return actions

- Status-change notifications and notification history (US-010)

### EPIC-07 — Digital Repository

- Search by LRN, name, grade level, and school year

- Record detail view

### EPIC-08 — Academic Analytics

- Section-level dashboard for Advisers; school-wide dashboard for Principal and Administrator

- Intervention flag list

### EPIC-09 — System Integration & Testing

- End-to-end integration across modules

- Functional, usability, performance, security, and compatibility testing (ISO/IEC 25010), consistent with the Proposal Manuscript's Testing Procedure

## 8.4 Product Backlog

| Story ID | User Story | Epic | Priority | Sprint |
| --- | --- | --- | --- | --- |
| US-001 | As a Subject Teacher, I want to log in securely so that I can access my assigned records. | Authentication | Must | Sprint 2 |
| US-002 | As a Subject Teacher, I want to upload official DepEd e-Class Records so that I do not re-enter grades. | Import | Must | Sprint 3 |
| US-003 | As a System, I want to consolidate grades using the student's LRN so that each learner has one complete academic record. | Consolidation | Must | Sprint 4 |
| US-004 | As a System, I want to validate grades before submission to ensure record accuracy. | Validation | Must | Sprint 5 |
| US-005 | As a System, I want to generate each learner's SF10 automatically from the validated consolidated record so that no one encodes it by hand; the Class Adviser and School Administrator preview and download it. | SF10 | Must | Sprint 6 |
| US-006 | As a Class Adviser, I want to review a consolidated class record and return one subject for correction so that errors are fixed by the teacher who entered them. | Submission Workflow | Must | Sprint 7 |
| US-007 | As a School Administrator, I want to approve or return a submitted class record so that only complete, accurate records reach the digital repository. | Submission Workflow | Must | Sprint 7 |
| US-008 | As a Principal, I want to view school-wide submission progress and analytics so that I can monitor academic performance without requesting manual reports. Records stay read-only for me; my one action is approving accounts (US-015). | Academic Analytics | Should | Sprint 8 |
| US-009 | As an Administrator, I want to assign Subject Teachers to specific (subject, section) pairs so that access stays restricted to what each teacher actually teaches. | Authentication | Must | Sprint 2 |
| US-010 | As any user, I want to receive a notification when my submission's status changes so that I do not need to check the system manually. | Submission Workflow | Should | Sprint 7 |
| US-011 | As a School Administrator, I want to set each section as Self-Contained or Departmentalized so that access matches how my school actually staffs each grade level, not a fixed assumption. | Authentication | Must | Sprint 2 |
| US-012 | As a Class Adviser, I want a performance dashboard and intervention flag list for my own section so that I can spot learners who need help early. | Academic Analytics | Should | Sprint 8 |
| US-013 | As a Class Adviser, I want to search the repository for learners in my own section by LRN, name, grade level or school year so that I can open their records quickly. | Digital Repository | Should | Sprint 7 |
| US-014 | As a Class Adviser or School Administrator, I want to enter a learner's grades from school years before EduCheck on their permanent record so that the SF10 covers every grade level. | SF10 | Should | Sprint 6 |
| US-015 | As a Principal, I want to approve or reject, with a reason, every new account and every role change that gives more access, so that the person who creates accounts is not the only one who grants access to learner records. Once I approve, the School Administrator finishes the setup and the temporary password is emailed to the user's DepEd address. | Authentication | Should | Sprint 9 |

(Continue expanding this backlog throughout development.)

# 9. Agile-Kanban Management

## 9.1 Sprint Plan

Each sprint will run for two weeks and end with a sprint review and adviser consultation.

## 9.2 Kanban Workflow

Product Backlog

↓

Ready

↓

In Progress

↓

Code Review

↓

Testing

↓

Done

## 9.3 Definition of Ready (DoR)

A user story is considered ready when:

- The user story is clearly written.

- Acceptance criteria are defined.

- Priority is assigned.

- Dependencies are identified.

- The team understands the requirement.

## 9.4 Definition of Done (DoD)

A feature is considered complete when:

- Development is finished.

- Code has been reviewed.

- Functional testing has passed.

- Documentation has been updated.

- The feature is demonstrated during the sprint review.

- The product owner (or adviser) accepts the completed work.

# 10. Quality Management

## 10.1 Coding Standards

- Camel case naming

- Meaningful variable and function names

- Modular architecture

- REST naming conventions

## 10.2 Code Review

Feature Branch

↓

Pull Request

↓

Review

↓

Testing

↓

Merge to Develop

↓

Merge to Main

## 10.3 Testing Strategy

- Unit Testing

- Functional Testing

- Integration Testing

- User Acceptance Testing

Aligned with the Functional, Usability, Performance, Security, and Compatibility testing defined in the Proposal Manuscript's Testing Procedure (ISO/IEC 25010).

# 11. Risk Management

| Risk | Probability | Impact | Mitigation |
| --- | --- | --- | --- |
| Excel format changes | Medium | High | Support only the official DepEd template used in the study. |
| Internet interruption | Medium | Medium | Offline status caching on mobile (M-10), refreshed when connectivity returns. |
| Delayed development | Medium | High | Prioritize must-have Product Backlog items. |
| Merge conflicts | Medium | Medium | Use Git branching and code reviews. |
| Database corruption | Low | High | Schedule regular database backups. |
| Incorrect subject/section assignment | Low | High | Administrator-only assignment control with a confirmation step and audit log. |
| Account email cannot be sent (no internet) | Medium | Low | The account is still activated; the Administrator hands over the temporary password shown on screen (Known Limitations L-06). |

# 12. Appendix

- Appendix A — Complete Product Backlog

- Appendix B — Entity-Relationship Diagram (ERD)

- Appendix C — API List

- Appendix D — UI Wireframes

- Appendix E — Sprint Templates

(To be attached as each is produced during development.)